## Sheet1
Remote Weather Monitoring and Forescasting
Batch - s3 Group g4
Date | Task | Sub Task | Progress
2024-04-03 | Designing | Login Page and Register Page | inProgress
|  | Home Page | inProgress
|  | Database Schema | inProgress
| Development | Local Server setup | Completed
|  | Database Creation | Completed
2024-04-10 | Designing | Login Page and Register Page | Completed
|  | Home Page | Completed
|  | Database Schema | Completed
| FrontEnd | Wepage Creation(HTML & CSS) | inProgress
| BackEnd | Database Tables Creation | Completed
|  | Fetch and Store data in tables from register & login page | inProgress
15-04-204 | FrontEnd | User Profile Page and Weather Page layout creation | Completed
|  | Wepage Creation(HTML & CSS) | Completed
| BackEnd | Fetch and Store data in tables from register & login page | Completed
|  | Fetch weather Data From API and update on page | inProgress
|  | User Session Management | inProgress
2024-04-17 | BackEnd | Fetch weather Data From API and update on page | Completed
|  | User Session Management | Completed
| Testing | Manual Testing on Database and webpages | inProgress